## Sheet1
task | start date | END DATE | DURATION
Database design | 2025-03-25 | 2025-03-27 | 2 days
user authentication | 2025-03-28 | 2025-03-30 | 2 days
inventory mansgement | 2025-03-31 | 2025-04-10 | 10days
order management | 2025-04-11 | 2025-04-15 | 4 days
Restocking and low stock alerts | 2025-04-16 | 2025-04-18 | 2 days
GUI development | 2025-04-19 | 2025-04-25 | 6 days
testing and debugging | 2025-04-26 | 2025-04-26 | 6 days
final touches and deployment | 2025-05-03 | 2025-05-07 | 4 days
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.